## Sheet1
Year | 2024
Month |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October
Calender week | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Project phases
Phase 1: Project Planning
Phase 2: Product Development
Phase 3: Marketing & Sales
Phase 4: Setting up for Launch
Phase 5: Post-Launch Fixes
Phase 6: Scaling
Define Project Scope, Assemble Team, Budgeting
Prototype Designing, Developing & Testing
Development of releaseable product out of prototype
Marketing campaigns and content distribution
Quality Assurance
Post-Launch Quality Assurance and Development (Hot-fixes)
Sales pitches & building customer relationship (B2B)
Agile Software Development
Infrastructure changes (organizational & technological) + New hirings
MS1: Prototype
MS2: PoseFix App 1.0
MS3: Launch (B2C)
MS4: B2B customers